## blog
Team Members
[6 empty] | First Name | Last Name | Nickname (max 6 characters)
[6 empty] | Bassil | Obeidi | BO
[6 empty] | Zulqarnain | Ali | ZA
[6 empty] | Toshani | Settvari | TS
[6 empty] | Fatima | Afzal | FA
[6 empty] | Dezirae | Asante | DA
Activities Table
Date | Who |  |  |  |  | Type of Activty | Number of hourse spent | Purpose | Output | Hours spent
| BO | ZA | TS | FA | DA |  |  |  |  | BO | ZA | TS | FA | DA
Milestone 1
2026-09-28 | 1 | 1 | 1 | 1 | 1 | In Person Meeting | 1 | Brainstorm Project Ideas | List of 3 software project ideas. | 1 | 1 | 1 | 1 | 1
2026-09-29 | 1 | 1 | 1 |  |  | Work at Home | 1 | Work on milestone 1 deliverables | Abstract, description and objectives | 1 | 1 | 1 | 0 | 0
2026-10-03 | 1 |  | 1 | 1 | 1 | Work at Home | 1 | Work on milestone 1 deliverables | Ethical Considerations and Formatting | 1 | 0 | 1 | 1 | 1
2026-10-03 | 1 |  |  |  |  | Work at Home | 0.5 | Format blog excel sheet | Blog/Work Hours tracker | 0.5 | 0 | 0 | 0 | 0
[9 empty] | Total hours | 3.5 | 2 | 3 | 2 | 2
[9 empty] | Total team hours | [5 empty] | 12.5
Milestone 2
2026-10-08 | 1 |  | 1 | 1 | 1 | Web-call | 1 | Assign tasks and align team | Task distribution | 1 | 0 | 1 | 1 | 1
2026-10-09 | 1 |  |  |  |  | Work at Home | 2 | Work on assigned Milestone 2 deliverables | updated product backlog | 2 | 0 | 0 | 0 | 0
2026-10-13 |  |  |  |  | 1 | Work at Home | 2 | Work on assigned Milestone 2 deliverables | Requirements Refinement | 0 | 0 | 0 | 0 | 2
2026-10-13 |  |  |  | 1 |  | Work at Home | 2 | Work on assigned Milestone 2 deliverables | Ethical Considerations (updated) | 0 | 0 | 0 | 2 | 0
2026-10-13 |  | 1 | 1 |  |  | Work at Home | 2 | Work on assigned Milestone 2 deliverables | Initial Design Sketches | 0 | 2 | 2 | 0 | 0
2026-10-13 | 1 |  |  |  |  | Work at Home | 0.75 | Updated Team Blog | Added appropriate entries for team blog, fixed formatting. | 0.75 | 0 | 0 | 0 | 0
[9 empty] | Total hours | 3.75 | 2 | 3 | 3 | 3
[9 empty] | Total team hours | [5 empty] | 14.75
Sprint 1
[10 empty] | 0 | 0 | 0 | 0 | 0
[9 empty] | Total hours | 0 | 0 | 0 | 0 | 0
[9 empty] | Total team hours | [5 empty] | 0
Sprint 2
[10 empty] | 0 | 0 | 0 | 0 | 0
[9 empty] | Total hours | 0 | 0 | 0 | 0 | 0
[9 empty] | Total Team hours | [5 empty] | 0
Sprint 3
[10 empty] | 0 | 0 | 0 | 0 | 0
[9 empty] | Total hours | 0 | 0 | 0 | 0 | 0
[9 empty] | total team hours | [5 empty] | 0
[9 empty] | Total hour over project | 7.25 | 4 | 6 | 5 | 5
[9 empty] | Total team hours over project | [5 empty] | 27.25