## Cover Page
Personalized Grocery and Diet Planning Application
Prepared By:
Team 03
Bassil Obeidi: 169074210
Zulqarnain Ali: 169076756
Fatima Afzal: 169085301
Dezirae Asante: 169096362
Toshani Settvari: 169083166

## Product Backlog
Product Backlog
Story ID | Story Title | Card | Story Points | Priority | Sprint | Status | Conversation | Confirmation
PROF-01 | User Onboarding and Contextualization | As a new user, I want to provide basic information and dietary goals during onboarding so that the application can personalize my experience. | 3 | High | Sprint 1 | Not Started | As per noted in the ethical considerations, customization should be opt in. Not providing information should not impact the features available to users, only the specificity of recommendations. Additionally, we should aim to diversify onboarding options, and ensure that customization and user preferences capture as wide a variety of personalities, goals and backgrounds as possible. | User can enter basic personal information and dietary goals during onboarding. User can skip providing onboarding information. Entered information is saved to the user's profile. The application uses the provided information to personalize subsequent functionality. The application remains usable when information is not provided.
PROF-02 | Nutritional Targets | As a user, I want to receive personalized calorie and macronutrient targets so that I have clear daily nutritional goals to work towards. | 3 | High | Sprint 1 | Not Started | Need to research how specifically these recommendations will be calculated. E.g. formula for daily maintenance calories etc. | Application calculates personalized daily calorie and macronutrient targets using the user's profile information and dietary goals. User can view their calculated targets. Targets include daily calorie, protein, carbohydrate, and fat targets. Targets update when relevant profile information or goals are changed.
PROF-03 | Preferences & restrictions | As a user, I want to specify my dietary preferences and restrictions so that the application can tailor its recommendations to me. | 5 | Medium | Sprint 3 | Not Started | Should be flexible as per ethical considerations | User can specify dietary preferences. User can specify dietary restrictions and allergies. Preferences and restrictions are saved to the user's profile. User can modify or remove previously specified preferences and restrictions. The application uses these settings when generating recommendations.
GROC-01 | Personalized Grocery Plan | As a user, I want the application to generate a personalized grocery list based on my dietary goals and preferences so that I can spend less time deciding what groceries to buy. | 13 | Medium | Sprint 2 | Not Started | Need to research how viable scraping food options from online grocery stores is. If not viable then a predefined list of grocery options should be compiled. | Application generates a grocery list based on the user's dietary goals and preferences. Generated items are relevant to the user's specified dietary restrictions. User can view the generated grocery list. User can add or remove items from the list. Grocery recommendations are still generated using reasonable defaults when relevant preferences are not provided.
GROC-02 | Adaptive Grocery Generation | As a user, I want the application to consider groceries I already have when generating my grocery list so that I do not have to purchase ingredients I already own. | 13 | Low | Sprint 3 | Not Started | Might require some type of database? | User can add groceries they currently have to their grocery inventory. User can remove or update items in their grocery inventory. Application considers the user's existing grocery inventory when generating a grocery list. Items already in the user's inventory are excluded or appropriately reduced from recommended purchases. User can view their current grocery inventory. Updated inventory is reflected in subsequent grocery recommendations.
MEAL-01 | Meal Suggestions | As a user, I want the application to suggest meals based on my dietary goals and preferences so that I can spend less time deciding what to eat. | 13 | Medium | Sprint 2 | Not Started | We need to research the viability of using generative AI, through something like an LLM api key to generate these meals. | Application generates meal suggestions based on the user's dietary goals and preferences. Suggested meals comply with specified dietary restrictions. User can view relevant nutritional information for suggested meals. User can select a suggested meal for further use or planning.
MEAL-02 | Adaptive Meal Suggestions | As a user, I want the application to consider groceries I have available or that have been recommended to me when suggesting meals so that I can make better use of the ingredients I have. | 21 | Low | Sprint 3 | Not Started | Same as MEAL-01. | Application uses the user's existing grocery inventory when generating meal suggestions. Application can also consider groceries included in the user's generated grocery list. Suggested meals make use of relevant available ingredients where appropriate. User can view which available ingredients are used by a suggested meal. Suggested meals continue to respect the user's dietary goals, preferences, and restrictions.
NUTR-01 | Nutritional Tracking | As a user, I want to track my nutritional consumption so that I can see how well my diet aligns with my nutritional goals. | 8 | Low | Future | Not Started | Daily macro tracker similar to apple health app, how it tracks steps? | User can record nutritional consumption. User can record individual foods or consumed meals. Recorded consumption includes relevant nutritional information. User can view their nutritional consumption for a given day. Application compares recorded consumption with the user's nutritional targets.
REP-01 | Historical Nutrition and Habit Tracking | As a user, I want to view historical information about my nutritional consumption and grocery spending so that I can identify trends in my habits over time. | 8 | Low | Future | Not Started | How exactly do we want to present this information to user. Need to decide whether pure data visualization works, or whether using AI to summarize the trends works. | User can view historical nutritional consumption. User can view historical grocery spending. Historical information can be viewed over different time periods. Application presents historical information in a way that allows users to identify trends. Historical records remain available for previously recorded data.
Legend:
UI: User Interface
PROF: User profile
MEAL: Meal planning
GROC: Grocery Planning
NUTR: Nutrition Tracking
REP: Reports/Analytics

## Sprint 1
Sprint 1 Backlog
Sprint 1 Goal(s): <Describe what you would like to achieve at the end of sprint 1>
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
UI-1 | UI-1.1 |  | <UI Epic 1, Task 1 description> |  | In Progress
UI-2 | UI-2.1 |  | <UI Epic 2, Task 1 description> |  | Completed
UI-2 | UI-2.2 |  | <UI Epic 2, Task 2 description> |  | Planned
COM-2 | COM-2.1 |  |  |  | Planned